## 2023
|  | Done | w/c 5 Jun |  |  |  |  | … | w/c 12 Jun |  |  |  |  | … | w/c 19 Jun |  |  |  |  | w/c 26 Jun |  |  |  |  | w/c 3 Jul |  |  |  |  | w/c 10 Jul |  |  |  |  | w/c 17 Jul |  |  |  |  | w/c 24 Jul |  |  |  |  | w/c 31 Jul |  |  |  |  | w/c 7 Aug |  |  |  |  | w/c 14 Aug |  |  |  |  | w/c 21 Aug |  |  |  |  | w/c 28 Aug |  |  |  |  | w/c 4 Sep |  |  |  |  | … | … | w/c 18 Sep
|  |  | 5 | 6 | 7 | 8 | 9 |  | 12 | 13 | 14 | 15 | 16 |  | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 31 | 1 | 4 | 5 | 6 | 7 | 8 |  |  | 18 | 19 | 20 | 21 | 22
Payroll | Final date for new staff contracts to be with HR | bar: w/c 3 Jul 5
Final review department monthly payroll - ensure correct account codes | bar: w/c 26 Jun 26 to w/c 3 Jul 5
Last date for overtime claims input | bar: w/c 10 Jul 12
| Final monthly payroll posting | N/A | bar: w/c 24 Jul 26
CCWS deadline to approve timesheets | bar: w/c 31 Jul 3
Final input for weekly payroll posting for 2022/23 YE | bar: w/c 31 Jul 31 to w/c 7 Aug 7
| Final weekly payroll posting for 2022/23 YE | N/A | bar: w/c 7 Aug 8
Final date for UPS input for 2022/23 (pay run 18 Aug) | bar: w/c 24 Jul 24 to w/c 7 Aug 10
Final Posting date for CCWS payroll | bar: w/c 7 Aug 11
| Final UPS payroll posting | N/A | bar: w/c 14 Aug 16
Accrue for costs to be included in2022/23 financial year that missed deadline | bar: w/c 28 Aug 30
Purchasing | Run and review Open Purchase Order report (Excel version) | bar: w/c 26 Jun 26 to w/c 31 Jul 31
Run and review Purchasing Requisition Status report | bar: w/c 26 Jun 26 to w/c 31 Jul 31
Complete, cancel or finally close open or incomplete POs and requisitions | bar: w/c 17 Jul 17 to w/c 7 Aug 7
Final date to process all PO transactions (NB PO close 5 pm) | bar: w/c 7 Aug 7
Accounts receivable | Identify and bank all cash, cheques received up until the end of July | bar: w/c 24 Jul 24 to w/c 31 Jul 31
| Module opened for 2023/24 financial year | N/A | bar: w/c 7 Aug 7
Process all cash, cheque and (if possible) PDQ receipts relating to 2022/23 | bar: w/c 24 Jul 24 to w/c 7 Aug 7
Last date for raising Internal Trading invoices and sending backing | bar: w/c 10 Jul 10 to w/c 7 Aug 10
Submit invoice write off forms to Credit Control | bar: w/c 31 Jul 31 to w/c 7 Aug 10
| Bank charges and small balance adjustments posted | N/A | bar: w/c 14 Aug 14
Review BACS lists and ensure all income for department has been receipted | bar: w/c 10 Jul 10 to w/c 14 Aug 14
Last date to receipt any remaining income, BACS or otherwise | bar: w/c 14 Aug 15
Raise, complete and dispatch all external AR invoices (NB AR closes 5pm) | bar: w/c 10 Jul 10 to w/c 14 Aug 15
Last date for issuing invoices to Group-defined organisations | bar: w/c 7 Aug 7 to w/c 14 Aug 15
| Departments notified of resolved Internal trading disputes | N/A | bar: w/c 14 Aug 15
| Full individual debt statements emailed to departments | N/A | bar: w/c 14 Aug 16
| 2023/24 internal trading invoices can be raised | N/A | bar: w/c 14 Aug 16
Last date to review for bad debts and notify Credit Control | bar: w/c 21 Aug 21 to w/c 21 Aug 25
| Final posting of bad debt provision | N/A | bar: w/c 28 Aug 29
Accounts Payable | Complete Cash Holding Confirmation form for balances as at 30 June | bar: w/c 17 Jul 20
| July Barclaycard statements available to print | N/A | bar: w/c 31 Jul 1
Submit 2022/23 AP items to Shared Services by 5 pm | bar: w/c 10 Jul 10 to w/c 7 Aug 8
All expenses, including Barclaycard, must be processed and approved in Concur | bar: w/c 10 Jul 10 to w/c 7 Aug 11
Clear all remaining Invoices on Hold | bar: w/c 10 Jul 10 to w/c 7 Aug 11
Process all remaining 2022/23 Internal Trading AP invoices | bar: w/c 10 Jul 10 to w/c 14 Aug 15
Process all remaining staff and visitor expenses | bar: w/c 10 Jul 10 to w/c 14 Aug 15
| Resolved Internal Trading disputes notified to Depts | N/A | bar: w/c 14 Aug 15
Process all remaining AP invoices (NB AP closes 5pm) | bar: w/c 10 Jul 10 to w/c 14 Aug 15
Inventory | Physical stocktake | bar: w/c 31 Jul 31
Update Inventory balances with results of stock take | bar: w/c 31 Jul 31 to w/c 7 Aug 7
Process all receipts and issues of stock up to 31 July (NB INV closes 5pm) | bar: w/c 31 Jul 31 to w/c 7 Aug 7
| Provide departments with inventory reconciliation | N/A | bar: w/c 7 Aug 8
Grants | Distribution of Grants Report (version 1) | N/A | bar: w/c 31 Jul 1
| Distribution of Grants Report (version 2) | N/A | bar: w/c 7 Aug 8
Review and clear grants fund check failures and exceptions | bar: w/c 31 Jul 31 to w/c 14 Aug 15
Correct research grant VAT errors | bar: w/c 31 Jul 31 to w/c 14 Aug 15
| Clear suspense account | N/A | bar: w/c 31 Jul 31 to w/c 14 Aug 15
Process monthly Barclaycard expenses before AP closes, if using this option | bar: w/c 31 Jul 31 to w/c 14 Aug 15
| Distribution of Grants Report (version 3) | N/A | bar: w/c 14 Aug 16
| Unreconciled suspense items cleared to department GL overhead accounts | N/A | bar: w/c 14 Aug 17
Unresolved Fund Check Failures cleared to original Grant | bar: w/c 14 Aug 17
Post EC PI time journals | bar: w/c 14 Aug 17
Finalise and release all research grants journals, including EC PI Time journals | bar: w/c 31 Jul 31 to w/c 14 Aug 17
Review final grants position BEFORE 5 pm (NB Grants close 5pm) | bar: w/c 31 Jul 31 to w/c 14 Aug 17
| Overheads and revenue re-run | N/A | bar: w/c 14 Aug 17
| Distribution of Grants Report (Final) | N/A | bar: w/c 14 Aug 18
Fixed Assets | Distribution of Fixed Asset Register as at 30 Jun to departments | N/A | bar: w/c 10 Jul 10
Review all departmental assets against the Fixed Asset Register | bar: w/c 10 Jul 10 to w/c 7 Aug 10
Physically verify assets against the Fixed Asset Register | bar: w/c 10 Jul 10 to w/c 7 Aug 10
Notify FA helpdesk of disposals/amendments | bar: w/c 10 Jul 10 to w/c 7 Aug 10
Return the amended departmental Fixed Asset Register | bar: w/c 7 Aug 10
| Exception spreadsheet sent out to departments | N/A | bar: w/c 14 Aug 16
Ensure that July not tracked additions are included on register | bar: w/c 14 Aug 16 to w/c 21 Aug 22
Notify FA helpdesk of July missed assets (Dept close) | bar: w/c 14 Aug 16 to w/c 21 Aug 23
| Central processing of all amendments to FA register (NB Module close 5pm) | N/A | bar: w/c 21 Aug 24
General Ledger | CUEF Units: last instructions to be received by Treasury & Investment Team for 22/23 | bar: w/c 31 Jul 1; w/c 7 Aug 8; w/c 14 Aug 15; w/c 21 Aug 22; w/c 21 Aug 24 to w/c 21 Aug 25
| July 2022 Chest Allocation (5 Postings plus Final) Budget field frozen in CUFS 24 Aug | N/A | bar: w/c 3 Jul 3; w/c 31 Jul 1; w/c 7 Aug 8; w/c 14 Aug 15; w/c 21 Aug 22; w/c 21 Aug 24 to w/c 21 Aug 25
Trust fund overheads posted (1st, 2nd, Final) | bar: w/c 31 Jul 1; w/c 14 Aug 17; w/c 28 Aug 31
Appropriations in Aid | bar: w/c 31 Jul 1
| Balance and post petty cash for 2022/23 | N/A | bar: w/c 31 Jul 3
Process Barclaycard expenses BEFORE AP close | bar: w/c 31 Jul 31 to w/c 14 Aug 15
| Carbon Reduction Charge (CRC) journal posted | N/A | bar: w/c 14 Aug 17
Last date for funds on deposit movement | bar: w/c 14 Aug 18
| EC PI Time adjustment | N/A | bar: w/c 14 Aug 18
| July CUEF distribution accrual and deposit account interest posted | N/A | bar: w/c 21 Aug 21
Clear trust fund deficits (Trust Fund Statement #2 issued 22 Aug) | bar: w/c 21 Aug 22 to w/c 21 Aug 24
| Final journal for Jul-23 VAT return adjustments that impact departments | N/A | bar: w/c 21 Aug 25
| CUEF valuation journal posted and departments notified | N/A | bar: w/c 28 Aug 30
Process journals for any remaining credit card expenditure | bar: w/c 14 Aug 14 to w/c 21 Aug 25; w/c 28 Aug 29 to w/c 28 Aug 30
Ensure expenditure is coded against same SoF as related income and clear deficits | bar: w/c 31 Jul 31 to w/c 21 Aug 25; w/c 28 Aug 29 to w/c 28 Aug 30
Complete spreadsheets for income and expense accruals - last date 1 Sep | bar: w/c 14 Aug 14 to w/c 21 Aug 25; w/c 28 Aug 29 to w/c 28 Aug 30
Process remaining departmental journals (NB GL closes 5 pm) | bar: w/c 31 Jul 31 to w/c 21 Aug 25; w/c 28 Aug 29 to w/c 28 Aug 30
| ICC overhead journals processed (Ver 1 and Final) | N/A | bar: w/c 31 Jul 1; w/c 28 Aug 31
| CUEF Revaluation posted for June and July (Into July GL period) | N/A | bar: w/c 4 Sep 7
| Actual July CUEF Distribution posted into Adjustment Period 1 | N/A | bar: w/c 4 Sep 7
Key Dates | NB Last CUEF unit trading date for 2022/23: June 19 | N/A
| Departmental Summary Reports (1, 2 & 3) - Final sent 7 Sept for YE certification | N/A | bar: w/c 31 Jul 2; w/c 21 Aug 22; w/c 28 Aug 1; w/c 4 Sep 7
| Trust Fund Statements (June, 1st, 2nd and Final) | N/A | bar: w/c 10 Jul 10; w/c 7 Aug 8; w/c 21 Aug 22; w/c 4 Sep 5
| Basic roll forward of balances | N/A | bar: w/c 4 Sep 5
| Special roll forward of balances | N/A | bar: w/c 4 Sep 7
| Departmental Certificate to be returned | N/A | bar: w/c 4 Sep 7 to w/c 4 Sep 8