## Sheet1
Month | Week commencing | Last date | Module | Action | Completed
JUNE | w/c 16 Jun | Thu 17 Jun | KeyDate | Last CUEF unit trading date for 2024/25
|  | Wed 18 Jun | AR | Final date to submit invoice write off forms to Credit Control >£25k
JUNE/JULY | w/c 30 Jun | Tue 1 Jul | GL | July 2025 Chest Allocation processed | N/A
|  | Fri 4 Jul | PAY | Final date for new staff contracts to be with HR
|  | Fri 4 Jul | PAY | Final review of institution monthly payroll - ensure correct account codes
JULY | w/c 7 Jul | Thu 10 Jul | FA | Distribution of Fixed Asset reports as at 30 Jun to institutions | N/A
|  | Thu 10 Jul | KeyDate | June Trust Fund statements sent out to institutions | N/A
|  | Fri 11 Jul | PAY | Last date for overtime claims input
| w/c 14 Jul | Fri 18 Jul | AP | Establish all petty cash balances, till floats and advance balances held as at 30 Jun and return Cash Holding Confirmation form
| w/c 21 Jul | Fri 25 Jul | PAY | Final monthly payroll posting | N/A
| w/c 28 Jul | Thu 31 Jul | AR | Identify and bank all cash and cheques received up until the end of July
|  | Thu 31 Jul | INV | Physical stock take for all institutions with stores
|  | Thu 31 Jul | PO | Run and review the Open Purchase Order Report - Excel Version
|  | Thu 31 Jul | PAY | Final approval of timesheets for Casual workers (pay run 15 August)
|  | Fri 1 Aug | GL | Indirect Cost Contribution (ICC) journal posted (Version 1) | N/A
|  | Fri 1 Aug | GMS | Distribution of Grants Report (version 1) | N/A
|  | Fri 1 Aug | GL | Trust Fund overheads posted (first posting) | N/A
|  | Fri 1 Aug | GL | July 2025 Chest Allocation (second posting) | N/A
|  | Fri 1 Aug | AP | July Barclaycard statements available | N/A
|  | Fri 1 Aug | GL | Appropriations in Aid (Trust Funds) | N/A
| w/c 4 August | Mon 4 Aug | KeyDate | Interim summary reports sent out to institutions (interim 1) | N/A
|  | Mon 4 Aug | PAY | Final input for weekly payroll posting 2024/25
|  | Tue 5 Aug | GL | Balance and post petty cash journal
|  | Tue 5 Aug | AR | Final date to submit invoice write off forms to credit control £10-£25k
|  | Wed 6 Aug | PAY | Final weekly payroll posting for 2024/25 YE | N/A
|  | Thu 7 Aug | PAY | Final date for UPS input for 2024/25 (pay run 15 Aug)
|  | Thu 7 Aug | AR | Process all cash, cheque and PDQ receipts relating to 2024/25 and run the Receipt Register report(s)
|  | Thu 7 Aug | KeyDate | Module opened for 2025/26 financial year | N/A
|  | Thu 7 Aug | INV | Process all Inventory transactions (NB INV closes 5pm)
|  | Thu 7 Aug | PO | Process all PO transactions (NB PO closes 5pm)
|  | Fri 8 Aug | KeyDate | 1st interim Trust Fund statement sent out to institutions | N/A
|  | Fri 8 Aug | AP | Submit 2024/25 AP items to Shared Services for processing by 5 pm
|  | Fri 8 Aug | GL | July 2025 Chest Allocation (Third Posting) | N/A
|  | Fri 8 Aug | KeyDate | Institutions provided with inventory reconciliation | N/A
|  | Fri 8 Aug | GMS | Distribution of Grants Report (version 2) | N/A
| w/c 11 Aug | Mon 11 Aug | PAY | Final posting date for CCWS payroll
|  | Tue 12 Aug | AR | Raise all July Internal Trading Invoices
|  | Tue 12 Aug | FA | Deadline for institutions to provide Fixed Asset Register
|  | Tue 12 Aug | FA | Review all institutional assets against the Fixed Asset Register
|  | Tue 12 Aug | FA | Physically verify assets against the Fixed Asset Register
|  | Tue 12 Aug | FA | Notify FA helpdesk of disposals/amendments
|  | Tue 12 Aug | AR | Final date to submit invoice write off forms to Credit Control <£10k
|  | Wed 13 Aug | PAY | Final UPS payroll posting into 2024/25
|  | Wed 13 Aug | AP | Clear all remaining "Invoices on hold"
|  | Wed 13 Aug | AP | Process all supplier invoices in SoftCo for the 2024/25 year end
|  | Wed 13 Aug | AP | Concur: All pre-August Barclaycard transactions to be coded in Concur and fully approved | N/A
|  | Thu 14 Aug | AR | Bank charges and small balance adjustments posted
|  | Fri 15 Aug | AR | Review BACS lists and ensure all income for your institution has been receipted
|  | Fri 15 Aug | AR | Last date to review and receipt any remaining income, BACS or otherwise, for your institution
|  | Fri 15 Aug | AR | Last date for issuing invoices to University Group-defined organisations
|  | Fri 15 Aug | AR | Raise, complete and dispatch all external AR invoices (NB AR closes 5pm)
|  | Fri 15 Aug | AP | In CUFS clear all remaining AP "invoices on hold"
|  | Fri 15 Aug | AP | In CUFS, recode all remaining Invoices on hold
|  | Fri 15 Aug | AP | Process all remaining 2024/25 Internal Trading AP invoices
|  | Fri 15 Aug | AP | Internal Trading disputes notified to Accounting Services
|  | Fri 15 Aug | AP | Process all staff and visitors’ expenses
|  | Fri 15 Aug | AP | Resolved Internal Trading disputes notified to institutions
|  | Fri 15 Aug | AP | Process all remaining AP invoices (NB AP closes 5pm) | N/A
|  | Fri 15 Aug | GL | July 2025 Chest Allocation (Fourth Posting)
|  | Fri 15 Aug | GMS | Review and clear research grant funds check failures and exceptions | N/A
|  | Fri 15 Aug | GMS | Correct research grant VAT errors
|  | Fri 15 Aug | GMS | Clear suspense grants on Grants module
| w/c 18 Aug | Mon 18 Aug | AR | Full individual debt statements emailed to institutions | N/A
|  | Mon 18 Aug | AR | First posting of bad debt provision | N/A
|  | Mon 18 Aug | KeyDate | 2024/25 internal trading invoices can be raised | N/A
|  | Mon 18 Aug | GMS | Unreconciled suspense items cleared to institution GL overhead accounts | N/A
|  | Mon 18 Aug | GMS | Distribution of Grants Report (version 3) | N/A
|  | Mon 18 Aug | FA | CRA to send out July additions not tracked report to institutions | N/A
|  | Tue 19 Aug | GMS | Post EC ‘PI Time’ journals on Grants module
|  | Tue 19 Aug | GMS | Finalise and release all research grants journals
|  | Tue 19 Aug | GMS | Unresolved Fund Check Failures cleared to original grant
|  | Tue 19 Aug | GMS | Overheads and revenue rerun (NB Grants closes 5pm) | N/A
|  | Tue 19 Aug | GMS | Review final grants position BEFORE 5pm (NB Grants closes 5pm)
|  | Tue 19 Aug | GL | Trust Fund overheads posted (2nd posting if appropriate) | N/A
|  | Wed 20 Aug | GL | Last date for funds on deposit movement
|  | Wed 20 Aug | GL | Post EC PI Time adjustment | N/A
|  | Wed 20 Aug | GMS | Distribution of Grants Report (version 4) | N/A
|  | Thu 21 Aug | GL | July CUEF distribution accrual and deposit account interest posted | N/A
|  | Thu 21 Aug | GL | Deposit account interest posted | N/A
|  | Fri 22 Aug | KeyDate | Interim Summary Reports emailed to institutions (interim report 2) | N/A
|  | Fri 22 Aug | KeyDate | Interim Trust Fund Statement sent out to institutions (interim report 2) | N/A
|  | Fri 22 Aug | FA | July not tracked additions included on the register
|  | Fri 22 Aug | GL | July 2025 Chest Allocation (Fifth Posting) | N/A
| w/c 25 Aug | Wed 27 Aug | FA | Process all amendments to FA register (NB FA closes 5pm)
|  | Wed 27 Aug | FA | Notify FA helpdesk of missed assets BEFORE 27 August
|  | Wed 27 Aug | GL | Clear any Trust Fund deficits based on a review of 2nd interim statements
|  | Thu 28 Aug | GL | Final journal for Jul-25 VAT return adjustments that impact institutions | N/A
|  | Thu 28 Aug | GL | July 2025 Chest Allocation (Final Posting) - Budget field frozen 28 Aug | N/A
|  | Fri 29 Aug | AR | Last date to review for bad debts and notify Credit Control
|  | Fri 29 Aug | AR | Final posting of bad debt provision | N/A
|  | Fri 29 Aug | PAY | Accrue for Payroll costs to be included in the Financial Year (missed deadline)
SEPTEMBER | w/c 1 Sep | Mon 1 Sep | GL | Accrue 31 July Concur expenses not processed through CUFS
|  | Mon 1 Sep | GL | CUEF valuation journal posted and institutions notified
|  | Mon 1 Sep | GL | Complete spreadsheets for income and expense accruals
|  | Mon 1 Sep | GL | Ensure expenditure is coded against the same SoF as related income, and clear deficits
|  | Mon 1 Sep | GL | Final date for sending GL journals for central processing (NB GL closes 5pm)
|  | Tue 2 Sep | GL | Final ICC journal posted | N/A
|  | Tue 2 Sep | GL | Final Trust Fund Overhead Journal posted | N/A
|  | Wed 3 Sep | KeyDate | Summary Reports - Interim 3 run and emailed to institutions | N/A
|  | Fri 5 Sep | KeyDate | Final Trust Fund statement sent out to institutions | N/A
|  | Fri 5 Sep | KeyDate | Roll forward of balances - basic | N/A
| w/c 8 Sep | Tue 9 Sep | GL | CUEF Revaluation posted for June and July (Into July GL period) | N/A
|  | Tue 9 Sep | GL | Actual July CUEF Distribution posted into Adjustment Period 1 | N/A
|  | Tue 9 Sep | KeyDate | Roll forward of balances – special | N/A
|  | Tue 9 Sep | KeyDate | Distribution of Year End Certificates to institutions | N/A
| w/c 22 Sep | Wed 24 Sep | KeyDate | Return signed year-end certificate(s)